## node
Docs | http://wukong.tclcom.com/ftp/pub/performance/perfeer/doc/
http://172.24.218.88/perfeer/web/community/
|  |  | deadline | remark
1 | first run | on going | 2016-11-25 | >app launch + call in out + antutu >upload+store db >showing chart
Detail showing next sheet

## A,TctPerfMonitorService
Perfeer TctPerfMonitorService
| update date | 2016-11-11
| android | TctPerfMonitor
| developer | jianhua.he@tcl.com
| Task ID | 3201165
| 详细开发笔记信息： | http://wukong.tclcom.com/ftp/pub/performance/TctPerfMonitorService_dev/dev/
|  | stats | deadline | simple remark | prop
1 | 框架 |  | DONE
2 | app launch time tracker |  | DONE | have bug here
3 | 来去电话 速度统计 | on going | 2016-11-15 |  | high
4 | fps tracker
5 | wake lock tracker |  |  | power consumption

## B,upload_apk
Perfeer upload apk
| update date | 2016-11-11
| android | upload apk
| developer | xiaobu.zhu@tcl.com
Task ID
|  | stats | deadline | simple remark
1 | 上传performance 数据到服务器 |  | 2016-11-25 | safeguard apk upload to server

## C,perfeer_web_showing
Perfeer web controller
| update date | 2016-11-11
| web | perfeer web controller | python html js css …
| developer | xiaobu.zhu@tcl.com | chao.wang@jrdcom.com
Task ID
| Test web addr | http://172.24.218.82:8002/
|  | stats | deadline | simple remark | author | prop
1 | first run 数据库存储 | on going | 2016-11-14 | one more interface; antutu冷冻字段未加 | xiaobo | high
2 | antutu数据解析显示 | on going | 2016-11-16 | antutu冷冻线未加 | wang chao | high
3 | app launch time数据解析显示 | on going | 2016-11-23 | 60% done; 实际数据未联调 | wang chao | high
4 | battery report showing | on going | 2016-12-31 | db + 解析 + showing FOR DOU | xiaobo | low